## Sprint Summary
MITO & TicketSir — Sprint 31-32 ¦ Executive Summary
Project Window: 15 Nov 2025 – 28 Apr 2026 ¦ As of 15 Apr 2026 ¦ Team: 7 members
TOTAL TASKS |  | COMPLETED |  | IN PROGRESS |  | NOT STARTED
43 |  | 17 |  | 17 |  | 9
EPIC / FEATURE STATUS
Epic / Feature | Status | Done | In Prog | Waiting | Avg % | Key Blockers / Notes
TicketSir | In Progress | 3 | 2 | 0 | 75% |  | T01 Bug Fixes not started; T05 DB Migration 80%
Rhemito | In Progress | 3 | 4 | 2 | 59% |  | T09 Notification Backend 70%; T13 Help Tickets 10%
Affiliate Dashboard | In Progress | 1 | 1 | 2 | 48% |  | T15 Design & T17 Frontend not started — BLOCKED
Role Based Login | Completed | 2 | 0 | 0 | 100% |  | —
OBO | In Progress | 1 | 1 | 0 | 83% |  | T22 Frontend at 65%
Rate Manager | In Progress | 2 | 2 | 1 | 54% |  | T26 Affiliate Migration not started; T27 FE at 20%
Customer Support | In Progress | 1 | 1 | 0 | 90% |  | T29 Frontend at 80%
Affiliate | In Progress | 1 | 2 | 1 | 70% |  | T32 Account Switching not started
MITO-Admin | Completed | 1 | 0 | 0 | 100% |  | —
Standalone | In Progress | 0 | 1 | 0 | 70% |  | T35 Help Tickets Mobile Update 70%
Testing | In Progress | 2 | 4 | 2 | 67% |  | T38, T42 not started; T40 OBO Testing 50%
OWNER WORKLOAD
Owner | Total | Done | In Prog | Waiting | Done % | Current Focus
Iyanu | 1 | 0 | 0 | 1 | 0% |  | 7986 Design — Not Started (BLOCKED)
Jayant | 8 | 3 | 4 | 0 | 38% |  | Biometric Login (95%), Notification Mobile (50%), Help Tickets Mobile (10%)
Monu | 11 | 5 | 5 | 1 | 45% |  | OBO FE (65%), Rate Manager FE (20%), Customer Support FE (80%)
Rishabh | 7 | 4 | 3 | 0 | 57% |  | DB Migration (80%), Notification Backend (70%), TicketSir Bug Fixes (0%)
Robin | 8 | 2 | 4 | 2 | 25% |  | Interswitch Testing (60%), OBO Testing (50%), DB Migration Testing (80%)
Sakshi | 9 | 6 | 2 | 1 | 67% |  | Rate Manager Cross Rates (80%), Interswitch-Payout (90%)
Vakil | 7 | 2 | 3 | 2 | 29% |  | OnePipe Enhancement (90%), Refund Enhancement (90%)
KEY DEPENDENCY RISKS (tasks blocked by unfinished predecessors)
Blocked Task | Depends On | Risk / Comment
T17 – 7986 Frontend: Web | T15 (Design), T16 (Backend) |  | Design NOT STARTED — Frontend completely blocked
T26 – Rate Manager Migration | T25 (Cross Rates) |  | Cross Rates 80% done; migration cannot start until complete
T42 – Help Tickets App Test | T35 (Mobile App Update) |  | Mobile update at 70%; testing will be delayed if not resolved
T11 – Notification Mobile | T09 (Backend 70%) |  | Mobile app 50% — backend must complete before mobile can finish
T38 – Date Caption Testing | T03 (Label Changes) |  | Label Changes Completed but testing still Not Started

## Task Tracker
MITO & TicketSir — Sprint 31-32 ¦ Project Tracker with Dependencies
Project Window: 15 Nov 2025 – 28 Apr 2026 ¦ Generated: 15 Apr 2026 ¦ Team: Iyanu · Jayant · Monu · Rishabh · Robin · Sakshi · Vakil
# | Task ID | Epic / Feature | Task Name | Owner | Status | Progress % | Start Date | End Date | Depends On | Dependency Description | Notes
TICKETSIR — 87% Complete
1 | T01 | TicketSir | TicketSir Bug Fixes | Rishabh | Not Started | 0% | 13-Feb-26 | 13-Feb-26 | —
2 | T02 | TicketSir | 7998 – Pre-sale & Waitlist Booking (Mobile) | Jayant | Completed | 100% | 24-Feb-26 | 24-Feb-26 | —
3 | T03 | TicketSir | Label Changes | Jayant | Completed | 100% | 24-Feb-26 | 24-Feb-26 | —
4 | T04 | TicketSir | 7839 – Biometric Login (TicketSir & Cokobar) | Jayant | In Progress | 95% | 10-Feb-26 | 24-Mar-26 | —
5 | T05 | TicketSir | 7923 – DB Migration of TicketSir | Rishabh | In Progress | 80% | 03-Mar-26 | 10-Apr-26 | —
RHEMITO — 77% Complete
6 | T06 | Rhemito | Rhemito Bug Fixes – Backend | Rishabh | Completed | 100% | 06-Feb-26 | 06-Feb-26 | —
7 | T07 | Rhemito | Rhemito Bug Fixes – Front end: Web | Monu | Completed | 100% | 19-Feb-26 | 02-Mar-26 | T06 | Frontend starts after Backend bug fix is done
8 | T08 | Rhemito | Rhemito Bug Fixes – Mobile App | Jayant | Completed | 100% | 25-Feb-26 | 06-Mar-26 | T06 | Mobile starts after Backend bug fix is done
9 | T09 | Rhemito | Notification – Backend | Rishabh | In Progress | 70% | 10-Apr-26 | 10-Apr-26 | —
10 | T10 | Rhemito | Notification – Front end: Web | Monu | Completed | 100% | 02-Apr-26 | 03-Apr-26 | T09 | Notification Web FE starts after Backend API ready
11 | T11 | Rhemito | Notification – Mobile App | Jayant | In Progress | 50% | 25-Mar-26 | 14-Apr-26 | T09 | Mobile notification starts after Backend API ready
12 | T12 | Rhemito | 7744 – Pay by Bank & Bank Transfer | Vakil | Not Started | 0% | 19-Feb-26 | 19-Feb-26 | —
13 | T13 | Rhemito | Rhemito-MobileApp: Help Tickets | Jayant | In Progress | 10% | 26-Mar-26 | 31-Mar-26 | —
14 | T14 | Rhemito | 8057: KYC Bug Fixes | Vakil | Not Started | 0% | 19-Feb-26 | 19-Feb-26 | —
AFFILIATE DASHBOARD — 80% Complete
15 | T15 | Affiliate Dashboard | 7986 – Design | Iyanu | Not Started | 0% | 12-Feb-26 | 12-Feb-26 | —
16 | T16 | Affiliate Dashboard | 7986 – Backend | Sakshi | Completed | 100% | 12-Feb-26 | 12-Feb-26 | —
17 | T17 | Affiliate Dashboard | 7986 – Frontend: Web | Monu | Not Started | 0% | 12-Feb-26 | 12-Feb-26 | T15, T16 | Frontend blocked on Design approval + Backend ready
18 | T18 | Affiliate Dashboard | OnePipe Enhancement | Vakil | In Progress | 90% | 19-Feb-26 | 10-Mar-26 | T16 | OnePipe Enhancement needs Backend (T16) complete
ROLE BASED LOGIN — 100% Complete
19 | T19 | Role Based Login | 7996 – Backend | Sakshi | Completed | 100% | 19-Feb-26 | 24-Mar-26 | —
20 | T20 | Role Based Login | 7996 – Frontend | Monu | Completed | 100% | 19-Feb-26 | 03-Mar-26 | T19 | Frontend login starts after Backend login API done
OBO — 85% Complete
21 | T21 | OBO | OBO – Backend | Rishabh | Completed | 100% | 19-Feb-26 | 01-Apr-26 | —
22 | T22 | OBO | OBO – Frontend | Monu | In Progress | 65% | 19-Feb-26 | 16-Mar-26 | T21 | OBO Frontend starts after OBO Backend ready
RATE MANAGER — 46% Complete
23 | T23 | Rate Manager | Backend – Config Setup | Sakshi | Completed | 100% | 09-Mar-26 | 16-Mar-26 | —
24 | T24 | Rate Manager | Backend – Overrides | Sakshi | Completed | 100% | 17-Mar-26 | 24-Mar-26 | T23 | Overrides config follows Config Setup completion
25 | T25 | Rate Manager | Backend – Cross Rates | Sakshi | In Progress | 80% | 25-Mar-26 | 10-Apr-26 | T24 | Cross Rates backend follows Overrides completion
26 | T26 | Rate Manager | Backend – Existing Affiliate Migration | Sakshi | Not Started | 0% | 14-Apr-26 | 28-Apr-26 | T25 | Affiliate Migration follows Cross Rates completion
27 | T27 | Rate Manager | Frontend | Monu | In Progress | 20% | 19-Feb-26 | 10-Apr-26 | T23 | Rate Manager FE starts after Config Setup (T23) done
CUSTOMER SUPPORT — 85% Complete
28 | T28 | Customer Support | Backend | Rishabh | Completed | 100% | 25-Mar-26 | 30-Mar-26 | —
29 | T29 | Customer Support | Front end | Monu | In Progress | 80% | 25-Mar-26 | 08-Apr-26 | T28 | Support Portal FE starts after Backend (T28) done
AFFILIATE — 88% Complete
30 | T30 | Affiliate | AirPeace Payment Pages / V2 Changes | Vakil | Completed | 100% | 19-Feb-26 | 19-Feb-26 | —
31 | T31 | Affiliate | Refund Enhancement | Vakil | In Progress | 90% | 26-Feb-26 | 26-Feb-26 | —
32 | T32 | Affiliate | Account Switching: Business ↔ Individual | Vakil | Not Started | 0% | 25-Feb-26 | 26-Feb-26 | —
33 | T33 | Affiliate | Interswitch-Payout | Sakshi | In Progress | 90% | 15-Nov-25 | 24-Feb-26 | —
MITO-ADMIN — 100% Complete
34 | T34 | MITO-Admin | 7811 – Movement to Retail Submission: Bug Fixes | Sakshi | Completed | 100% | 19-Feb-26 | 19-Feb-26 | —
STANDALONE — 70% Complete
35 | T35 | Standalone | Help Tickets Mobile App (Update) | Jayant | In Progress | 70% | 26-Mar-26 | 08-Apr-26 | T13 | Mobile app update follows initial Help Tickets dev (T13)
TESTING — 73% Complete
36 | T36 | Testing | 7925 – Interswitch Testing | Robin | In Progress | 60% | 20-Mar-26 | 03-Apr-26 | T33 | Interswitch Testing starts after payout (T33) complete
37 | T37 | Testing | 8002: TicketSir Pre-sale & Waitlist App Testing | Robin | Completed | 100% | 25-Feb-26 | 25-Feb-26 | T02 | Testing starts after pre-sale feature (T02) complete
38 | T38 | Testing | 8054: Date Caption Changes Testing | Robin | Not Started | 0% | 26-Feb-26 | 26-Feb-26 | T03 | Testing starts after label changes (T03) complete
39 | T39 | Testing | Role Based Testing | Robin | Completed | 100% | 13-Mar-26 | 24-Mar-26 | T19, T20 | Role Based Testing after Backend + Frontend complete
40 | T40 | Testing | OBO Testing | Robin | In Progress | 50% | 18-Mar-26 | 14-Apr-26 | T21, T22 | OBO Testing after Backend + Frontend complete
41 | T41 | Testing | Help Tickets Web Testing | Robin | In Progress | 75% | 03-Apr-26 | 08-Apr-26 | T29 | Help Tickets Web Testing after portal FE (T29) done
42 | T42 | Testing | Help Tickets App Testing | Robin | Not Started | 0% | 08-Apr-26 | 09-Apr-26 | T35 | Help Tickets App Testing after mobile update (T35) done
43 | T43 | Testing | TicketSir DB Migration Testing | Robin | In Progress | 80% | 13-Mar-26 | 10-Apr-26 | T05 | DB Migration Testing after DB Migration (T05) complete
SPRINT TOTALS |  |  |  |  | 17 Completed ¦ 17 In Progress ¦ 9 Not Started |  | 66.4%
DEPENDENCY RULES: Frontend -> Backend ¦ Design -> Frontend ¦ Testing -> Implementation ¦ Rate Manager: Config Setup -> Overrides -> Cross Rates -> Migration ¦ Depends On: dash = No prerequisite task

## Summary Dashboard
MITO & TicketSir – Sprint 31-32 ¦ Summary Dashboard
As of 15 Apr 2026 — Project Window: 15 Nov 2025 – 28 Apr 2026
TOTAL TASKS |  |  | COMPLETED |  | IN PROGRESS |  | NOT STARTED
43 |  |  | 17 |  | 17 |  | 9
EPIC / FEATURE STATUS
Epic / Feature | Tasks | Completed | In Progress | Not Started | Avg Progress % | Status | Blocking Tasks
TicketSir | 5 | 3 | 2 | 0 | 75% | In Progress | T01 (Bug Fixes), T05 (DB Migration)
Rhemito | 9 | 3 | 4 | 2 | 59% | In Progress | T09 (Notification Backend), T11, T13
Affiliate Dashboard | 4 | 1 | 1 | 2 | 48% | In Progress | T15 (Design), T17 (Frontend)
Role Based Login | 2 | 2 | 0 | 0 | 100% | Completed | —
OBO | 2 | 1 | 1 | 0 | 83% | In Progress | T22 (Frontend at 65%)
Rate Manager | 5 | 2 | 2 | 1 | 54% | In Progress | T26 (Affiliate Migration), T27 (FE)
Customer Support | 2 | 1 | 1 | 0 | 90% | In Progress | T29 (Frontend at 80%)
Affiliate | 4 | 1 | 2 | 1 | 70% | In Progress | T32 (Account Switching)
MITO-Admin | 1 | 1 | 0 | 0 | 100% | Completed | —
Standalone | 1 | 0 | 1 | 0 | 70% | In Progress | T35 (Mobile Update)
Testing | 8 | 2 | 4 | 2 | 67% | In Progress | T38 (Date Caption), T42 (App Testing)
OWNER WORKLOAD SUMMARY
Owner | Total Tasks | Completed | In Progress | Not Started | Completion % | Active Epics
Iyanu | 1 | 0 | 0 | 1 | 0% | Affiliate Dashboard (Design)
Jayant | 8 | 3 | 4 | 0 | 38% | TicketSir, Rhemito, Standalone
Monu | 11 | 5 | 5 | 1 | 45% | Rhemito, OBO, Rate Manager, Customer Support, Role Based
Rishabh | 7 | 4 | 3 | 0 | 57% | TicketSir, Rhemito, OBO, Customer Support
Robin | 8 | 2 | 4 | 2 | 25% | Testing (all streams)
Sakshi | 9 | 6 | 2 | 1 | 67% | Rate Manager, Affiliate, Role Based, MITO-Admin
Vakil | 7 | 2 | 3 | 2 | 29% | Affiliate Dashboard, Affiliate, Rhemito